## Sheet1
Month | weeks | Task
September | 4 | Idea selection
October | 4 | Literature survey
November | 4 | Software requirement,Modules,Library and documents selection
December | 4 | Audio reception and condition algorithm
January | 4 | 3d representation and stft of audio signal
February |  | Mathematical modelling of musical notes
March |  | Database building
App developement

## Sheet2
ab
12
34
56
78

## Sheet3
Month | September | October | November | December | January | February | March
Week

## Sheet4
Month | September |  |  |  | october |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | Febuary |  |  |  | March
Week | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Idea Selection
Literature survey
Software requirement ,Modules Library and document selection
Audio reception and conditioning algorithm
3D representation and STFT on Audio signal
Mathematical modelling on musical notes
Database building
Application development